## KPI Summary
Metric | Value
Tasks tracked (active register) | 16
Tasks done | 4
Tasks in progress | 7
Tasks not started | 5
On-time completion rate, latest week | 87%
On-time completion rate, change vs. prior week | +0 pts
Average occupancy, monitored floors | 66.2%
Peak occupancy day | Wed (93%)
Floors/days at or above risk threshold | 2

## Task Register
name | owner | priority | status | due | link
Reconcile Q3 vendor statements | Accounting | Urgent | In progress | 2026-09-12 | Reduce reconciliation exceptions
Draft monthly close scorecard template | Business Support | Important | Done | 2026-09-05 | Standardize monthly close reporting
Coordinate desk audit for Floor 14 | Real Estate | Urgent | In progress | 2026-09-11 | Floor 14 reconfiguration
Migrate legacy SOPs into shared workspace | Business Support | Important | In progress | 2026-09-18 | Consolidate documentation
Validate automated batch import rules | Technology | Urgent | Not started | 2026-09-10 | Reduce reconciliation exceptions
Confirm AV install schedule | Technology | Important | Not started | 2026-09-24 | Floor 14 reconfiguration
Build stakeholder scorecard automation | Business Support | Medium | In progress | 2026-09-25 | Stakeholder scorecard automation
Facilitate cross-team requirements workshop | Leadership | Important | Done | 2026-09-03 | Standardize monthly close reporting
Update floor plan schematics | Facilities | Medium | In progress | 2026-09-14 | Floor 14 reconfiguration
Archive superseded documentation versions | Business Support | Low | Done | 2026-08-29 | Consolidate documentation
UAT: new expense-approval workflow | Technology | Urgent | In progress | 2026-09-15 | Reduce reconciliation exceptions
Prepare leadership business review deck | Business Support | Important | Not started | 2026-09-22 | Overview scorecard
Audit access controls on shared workspace | Technology | Urgent | Not started | 2026-09-12 | Access control audit
Draft SOP for new vendor onboarding | Accounting | Medium | In progress | 2026-09-19 | New vendor onboarding SOP
Weekly reconciliation exception review | Accounting | Low | Done | 2026-09-06 | Reduce reconciliation exceptions
Send occupant move-in communications | Business Support | Medium | Not started | 2026-11-10 | Floor 14 reconfiguration

## Status x Priority Pivot
status | Urgent | Important | Medium | Low | Total
Not started | 2 | 2 | 1 | 0 | 5
In progress | 3 | 1 | 3 | 0 | 7
Done | 0 | 2 | 0 | 2 | 4
Total | 5 | 5 | 4 | 2 | 16

## Overdue Open Items
name | owner | priority | status | due

## Volume by Function
function | count | share_pct | cumulative_share_pct
Business Support | 22 | 32.4 | 32.4
Accounting | 14 | 20.6 | 53
Technology | 13 | 19.1 | 72.1
Facilities | 8 | 11.8 | 83.9
Real Estate | 6 | 8.8 | 92.7
Leadership | 5 | 7.4 | 100.1

## Completion Trend
week | on_time_pct | change_pts | rolling_4wk_avg
Wk1 | 74
Wk2 | 78 | 4
Wk3 | 81 | 3
Wk4 | 79 | -2 | 78
Wk5 | 85 | 6 | 80.8
Wk6 | 83 | -2 | 82
Wk7 | 87 | 4 | 83.5
Wk8 | 87 | 0 | 85.5